Title
Using MS Project to plan the construction of a solar power station
Roderick MacKenzie
Imperial College London, Department of Physics, London SW7 2AZ, United Kingdom

---
What is MS Project?
It is a tool to help you run large projects. It helps you:
  - Assign resources to tasks
  - Track the progress of your project
  - Manage your budget
  - Analyze Workloads
http://en.wikipedia.org/wiki/Microsoft_Project

---
We are going to build a:
Molten salt solar power station
Picture: Barstow, CA; Solar One, NREL
http://edition.cnn.com/video/?/video/international/2011/10/02/ecosolutions-spain-solar-plant.cnn

---
How does it work?
http://edition.cnn.com/video/?/video/international/2011/10/02/ecosolutions-spain-solar-plant.cnn

---
Interesting facts about solar energy.
There is a lot of energy in sunlight
Max power flux 1.5 kW m-2
Typical solar cell efficiency 15%
Average electricity demand per person is in the UK is 700 W we therefore need 40 m2 per person.
Photo: Martin Abegglen

---
Planning our project
Tasks:
Clearing land of rocks
Install foundations
Install supports for mirrors
Construct tower
Install salt pumping equipment
Install computer control equipment
Connect to grid

---
Planning our project
Resources:
Bulldozers
Concrete pumps
Mettle working team
Turbine installation team
Electrical Engineers

---
Making a new project
Run MS Project then:
Click on file
New
Blank project
1
3
2

---
Our blank project
Double click on the first row

---
Adding our first task
Time it lasts
Task name

---
Building the project task-by-task
The task
Duration
First bar on gantt chart

---
Add the duration of all the tasks

---
The project plan will look like this

---
Setting task dependencies (links)
Drag drop arrows between the bars to link the tasks

---
Adding resources to the proejct

---
Assigning resources to our tasks

---
Select the resource to assign

---
We have assigned the resources but the mettle working team has too much work

---
Go back to the Task information box and reduce the work load for the mettle working team.
Click on Units and reduce it to 50%

---
Now we are not overworking the mettle working team.

---
Adding a mile stone:
This is a task with no length

---
Adding costs for the resources

---
Add a new column called costs
Right click and add Costs

---
Critical path analysis
A critical path finds tasks which if delayed will extend the duration of the project.

---
Your turn!
Your task is to plan the construction of an Offshore wind farm. The details can be found on moodle.
Image: Martin Pettitt